EXECUTION FAILURE DIAGNOSTIC

EPM-JO Bootcamp · PMI Jordan Chapter × INJAZ mySTARTUP · Session 1 handout · Trainer: Deeb Haddad, PMP

Execution failure can be diagnosed. Every failure pattern shows early symptoms. Project management spots them early (discovery) and acts on them (resolution).

| # | Pattern | Early symptom | Discover it with (PM practice) | Resolve it with (PM practice) | CAPM domain |
| --- | --- | --- | --- | --- | --- |
| F1 | Building the wrong thing | Features shipped, few paying users | Needs assessment; stakeholder analysis; interviews (elicitation) | Problem statement; acceptance criteria; test before building | Business analysis |
| F2 | Cash runs out before evidence | Nobody can state the monthly burn or the runway | Cost baseline; planned vs. actual spend | Spend per proven milestone; runway = cash ÷ net monthly burn | Predictive |
| F3 | Everything urgent, nothing finished | Many tasks in progress, few done | Visible backlog; Kanban board | MoSCoW; work-in-progress limit; one sprint goal | Agile |
| F4 | Nobody owns it / founder deadlock | Tasks fall between founders; the same arguments repeat | RACI (responsibility matrix) | One accountable owner; decision rights; escalation rule | Fundamentals |
| F5 | Surprises that block launch | Launch stopped by a legal, tax, data or supplier issue | Risk identification; assumption and constraint log | Risk register with owner, response and trigger | Fundamentals; predictive |

Global data, not Jordan statistics: CB Insights (2021, 111 startup post-mortems) — founders cited running out of cash or failing to raise (38%) and no market need (35%) as top reasons. Running out of cash is usually a symptom (F2) of F1, F3 or F4.

| Three types of work • Project — temporary, unique result (MVP v1, registration, a pilot) • Operation — ongoing and repeated (support, accounting, deliveries) • Experiment — a small test to learn, then decide | Approach by stage • Idea / validation → experiments • MVP → agile sprints inside fixed milestones • Operating → hybrid: fixed = legal, tax (e.g. JoFotara), contracts, funder milestones; flexible = features |
| --- | --- |

Where each pattern is solved today

F2 → Session 2 (plan and budget) · F1 → Session 3 (assumption testing) · F3 → Sessions 4 and 6 (backlog, rhythm) · F4 and F5 → Session 5 (risks, roles, decision rights)

Framework: trainer's synthesis of CB Insights post-mortem data and PMI practice (PMBOK® Guide, Agile Practice Guide, CAPM exam content outline). Handbook: nxemtech-startup.nextmtech.com